## COOPEGUANACASTE
Start Date: |  | 05/06/26
TC ID | Test Case Name | Priority | Steps | Page Objects Required | Status | Est. Effort (Hours) | Work-Days | Estimated Date
TC-01 | Residential Account Creation | P1 | 1 | None (use existing) | ✅ Automated | 0 | 0 | -
TC-02 | Installation Invoice Payment | P1 | 1 | None (use existing) | ✅ Automated | 0 | 0 | -
TC-03 | Successful Provisioning | P1 | 12 | customer-hub/customer-management/customer-management.page.ts, customer-hub/order-management/order-management.page.ts, customer-hub/customer-management/account-details/subscription-data/services.page.ts | ✅ Automated | 0 | 0 | -
TC-04 | Grace Period Billing | P1 | 3 | operations-hub/jobs-management/jobs-management.page.ts [NEW] | ⏳ Pending | 6 | 0.75 | 08/06/26
TC-05 | Recurring Billing Month 01 | P1 | 3 | operations-hub/jobs-management/jobs-management.page.ts [NEW] | ⏳ Pending | 6 | 0.75 | 09/06/26
TC-06 | Recurring Billing Month 02 | P1 | 3 | operations-hub/jobs-management/jobs-management.page.ts [NEW] | ⏳ Pending | 6 | 0.75 | 10/06/26
TC-07 | Collection Notification Month 02 | P1 | 6 | operations-hub/jobs-management/jobs-management.page.ts [NEW], ar-hub/collections/collection-agents/accounts-in-collection.page.ts [NEW] | ⏳ Pending | 13.5 | 1.69 | 11/06/26
TC-08 | Full Billing, Collections, Notifications, Suspension and Reconnection Flow (Month 01 to Month 05) | P1 | 20 | operations-hub/jobs-management/jobs-management.page.ts [NEW], ar-hub/ar-operations/ar-operations/adjustment.page.ts [NEW], ar-hub/collections/collection-agents/accounts-in-collection.page.ts [NEW], customer-hub/customer-management/account-details/subscription-data/services.page.ts | ⏳ Pending | 24.5 | 3.06 | 16/06/26
TC-09 | Validate Full Collections Flow with Payments, Billing and Plan Change | P1 | 13 | ar-hub/collections/collection-agents/accounts-in-collection.page.ts [NEW] | ⏳ Pending | 11 | 1.38 | 18/06/26
TC-10 | Validate Full Residential Account Grace Period (Extension) Flow | P3 | 12 | ar-hub/collections/collection-agents/accounts-in-collection.page.ts [NEW] | ⏳ Pending | 12.5 | 1.56 | 19/06/26
TC-TEMP-11 | Validate Full Residential Account Grace Period (Extension) Flow | P2 | 6 | ar-hub/collections/collection-agents/accounts-in-collection.page.ts [NEW], customer-hub/customer-management/customer-management.page.ts, customer-hub/customer-management/account-details/billing-data/bills.page.ts, customer-hub/customer-management/account-details/account-data/payment-installment.page.ts [NEW] | ⏳ Pending | 13.5 | 1.69 | 23/06/26
TC-11 | Validate Credit Note Flow | P2 | 9 | ar-hub/ar-operations/ar-operations/adjustment.page.ts [NEW], ar-hub/collections/collection-agents/accounts-in-collection.page.ts [NEW] | ⏳ Pending | 15 | 1.88 | 25/06/26
TC-12 | Validate Debit Note Flow | P3 | 9 | ar-hub/ar-operations/ar-operations/adjustment.page.ts [NEW], ar-hub/collections/collection-agents/accounts-in-collection.page.ts [NEW] | ⏳ Pending | 15 | 1.88 | 29/06/26
TC-13 | Validate Equipment Retrieval (Cancellation) Order Flow | P2 | 14 | ar-hub/collections/collection-agents/accounts-in-collection.page.ts [NEW] | ⏳ Pending | 13.5 | 1.69 | 01/07/26
TC-14 | Intercompany Residential Account End-to-End Flow | P2 | 15 | None (use existing) | ⏳ Pending | 10 | 1.25 | 02/07/26
TC-15 | Residential Account with Tax Exemption Validation | P3 | 12 | customer-hub/customer-management/customer-management.page.ts, customer-hub/customer-management/account-details/billing-data/bills.page.ts, customer-hub/customer-management/account-details/account-data/payment-installment.page.ts [NEW], customer-hub/customer-management/account-details/account-data/custom-attributes.page.ts [NEW] | ⏳ Pending | 16.5 | 2.06 | 06/07/26
TC-16 | PHC Account Creation with Required Bundles | P3 | 11 | None (use existing) | ⏳ Pending | 8 | 1 | 07/07/26
TC17 | Subscription Data / Offers – Filter Active Offers | P1 | 7 | customer-hub/customer-management/account-details/subscription-data/services.page.ts | ⏳ Pending | 4 | 0.5 | 07/07/26
TC66 | Account Data / Tasks – Installment Payment Plan Creation | P1 | 6 | None (use existing) | ⏳ Pending | 3.5 | 0.44 | 08/07/26
TOTAL |  |  |  |  | 3 Done / 16 Pending |  |  | 08/07/26

## EMBRIX
Start Date: |  | 08/07/26
TC ID | Test Case Name | Priority | Steps | Page Objects Required | Status | Est. Effort (Hours) | Work-Days | Estimated Date
TC-18 | Residential Account and Order Creation with Internet Bundle | P1 | 34 | customer-hub/customer-management/customer-management.page.ts, customer-hub/order-management/order-management.page.ts | ⏳ Pending | 17.5 | 2.19 | 13/07/26
TC19 | Create Quotation in Embrix | P3 | 24 | pricing-hub/pricing-management/pricing-catalog/product-family.page.ts [NEW], customer-hub/customer-management/customer-management.page.ts | ⏳ Pending | 16.5 | 2.06 | 15/07/26
TC20 | Send Existing Order from Order Management | P1 | 12 | customer-hub/customer-management/customer-management.page.ts, customer-hub/order-management/order-management.page.ts | ⏳ Pending | 6.5 | 0.81 | 16/07/26
TC21 | Invoice Consultation and Validation in Billing Center | P2 | 18 | billing-hub/billing/bulk-operations/bulk-operations.page.ts [NEW], customer-hub/customer-management/account-details/billing-data/bills.page.ts, customer-hub/customer-management/account-details/account-data/payment-installment.page.ts [NEW] | ⏳ Pending | 17.5 | 2.19 | 20/07/26
TC22 | Billing Center / Taxes – Tax Code Configuration | P3 | 24 | billing-hub/taxation/tax-code-config.page.ts [NEW] | ⏳ Pending | 16.5 | 2.06 | 22/07/26
TC23 | Billing Center – Usage | P3 | 19 | billing-hub/usage/usage-config.page.ts [NEW] | ⏳ Pending | 14 | 1.75 | 24/07/26
TC24 | Pricing Center – Basic Configurations (Currency) | P1 | 12 | pricing-hub/base-configurations/resources/currency.page.ts [NEW] | ⏳ Pending | 10.5 | 1.31 | 27/07/26
TC25 | Pricing Center – Price Management (Product Family) | P3 | 11 | pricing-hub/pricing-management/pricing-catalog/product-family.page.ts [NEW] | ⏳ Pending | 10 | 1.25 | 28/07/26
TC26 | Pricing Center – Package Management | P1 | 4 | pricing-hub/bundle-management/package.page.ts [NEW] | ⏳ Pending | 6.5 | 0.81 | 29/07/26
TC27 | Payment History Inquiry in A/R Center | P3 | 12 | ar-hub/payments/payment-operations/payment-history.page.ts [NEW] | ⏳ Pending | 10.5 | 1.31 | 30/07/26
TC28 | View Invoice Units in Collections | P1 | 12 | ar-hub/collections/collection-agents/accounts-in-collection.page.ts [NEW] | ⏳ Pending | 10.5 | 1.31 | 03/08/26
TC29 | A/R Center Flow Validation | P3 | 22 | ar-hub/ar-operations/ar-operations/adjustment.page.ts [NEW], ar-hub/ar-operations/ar-operations/disputes.page.ts [NEW], ar-hub/ar-operations/ar-operations/write-offs.page.ts [NEW] | ⏳ Pending | 15.5 | 1.94 | 04/08/26
TC30 | Revenue Center / Configuration | P3 | 7 | revenue-hub/configuration/multi-org-setup/locations.page.ts [NEW], revenue-hub/configuration/base-configurations/gl-setup.page.ts [NEW] | ⏳ Pending | 8 | 1 | 05/08/26
TC31 | Revenue Center / Revenues | P3 | 11 | revenue-hub/revenue/journals.page.ts [NEW], revenue-hub/revenue/accounting-log.page.ts [NEW] | ⏳ Pending | 10 | 1.25 | 07/08/26
TC32 | Operations Center / User Management – Successful Creation and Modification | P1 | 13 | operations-hub/user-management/users.page.ts [NEW], customer-hub/customer-management/account-details/account-data/contact.page.ts [NEW], customer-hub/customer-management/account-details/account-data/addresses.page.ts [NEW] | ⏳ Pending | 19 | 2.38 | 11/08/26
TC33 | Operations Center / Work Management – Work Calendar Information Validation | P1 | 4 | operations-hub/jobs-management/jobs-management.page.ts [NEW] | ⏳ Pending | 6.5 | 0.81 | 12/08/26
TC34 | Operations Center / Correspondence – Template Configuration and Download Validation | P2 | 6 | operations-hub/correspondence/templates.page.ts [NEW] | ⏳ Pending | 7.5 | 0.94 | 13/08/26
TC35 | Operations Center / Reports – Accounts Report Validation | P1 | 7 | operations-hub/reports/reports.page.ts [NEW] | ⏳ Pending | 8 | 1 | 14/08/26
TC36 | Operations Center / Instance Management – Successful Modification | P3 | 11 | operations-hub/tenant-management/tenant-data.page.ts [NEW] | ⏳ Pending | 12 | 1.5 | 17/08/26
TC37 | Operations Center / Task Administration – Successful Task Creation | P3 | 11 | operations-hub/task-management/tasks.page.ts [NEW] | ⏳ Pending | 10 | 1.25 | 19/08/26
TC38 | Account Data / Account Information – Customer Segment Modification | P1 | 8 | customer-hub/customer-management/account-details/account-data/account-info.page.ts | ⏳ Pending | 4.5 | 0.56 | 19/08/26
TC39 | Account Data / Contact – Contact Modification and Creation | P1 | 8 | customer-hub/customer-management/account-details/account-data/contact.page.ts [NEW] | ⏳ Pending | 8.5 | 1.06 | 20/08/26
TC40 | Account Data / Addresses – Address Creation and Modification | P1 | 10 | customer-hub/customer-management/account-details/account-data/addresses.page.ts [NEW] | ⏳ Pending | 9.5 | 1.19 | 21/08/26
TC41 | Account Data / Payment Profile – Payment Method Modification | P1 | 9 | customer-hub/customer-management/account-details/account-data/payment-profile.page.ts [NEW] | ⏳ Pending | 9 | 1.13 | 25/08/26
TC42 | Account Data / Billing Profile – Annual Billing Modification | P1 | 8 | customer-hub/customer-management/account-details/account-data/billing-profile.page.ts [NEW] | ⏳ Pending | 8.5 | 1.06 | 26/08/26
TC43 | Account Data / Custom Attributes & Tax Exemptions – Configuration and Modification | P2 | 18 | customer-hub/customer-management/account-details/account-data/custom-attributes.page.ts [NEW] | ⏳ Pending | 13.5 | 1.69 | 27/08/26
TC44 | Account Data / Hierarchy – Move Account to Parent Hierarchy | P3 | 12 | customer-hub/customer-management/account-details/account-data/payment-profile.page.ts [NEW], customer-hub/customer-management/account-details/account-data/hierarchy.page.ts [NEW] | ⏳ Pending | 14.5 | 1.81 | 31/08/26
TC45 | Account Data / Tasks – Installment Payment Plan Creation | P1 | 6 | None (use existing) | ⏳ Pending | 3.5 | 0.44 | 01/09/26
TC46 | Account Data / Exchange Rates – External Purchase Order Configuration | P3 | 16 | customer-hub/customer-management/account-details/account-data/xchange-rates.page.ts [NEW] | ⏳ Pending | 12.5 | 1.56 | 02/09/26
TC47 | Subscription Data / Subscription View – Active Subscription Detail | P2 | 7 | customer-hub/customer-management/account-details/subscription-data/services.page.ts | ⏳ Pending | 4 | 0.5 | 03/09/26
TC48 | Subscription Data / Services – Service Creation and Order Approval | P2 | 10 | customer-hub/customer-management/account-details/subscription-data/services.page.ts | ⏳ Pending | 5.5 | 0.69 | 03/09/26
TC49 | Subscription Data / Offers – Filter Active Offers | P1 | 7 | customer-hub/customer-management/account-details/subscription-data/services.page.ts | ⏳ Pending | 4 | 0.5 | 04/09/26
TC50 | Subscription Data / Billable Services – Filter and Export | P3 | 6 | customer-hub/customer-management/account-details/subscription-data/services.page.ts | ⏳ Pending | 3.5 | 0.44 | 04/09/26
TC51 | Subscription Data / Provisioning Inquiry – View Provisioning Data | P2 | 5 | None (use existing) | ⏳ Pending | 3 | 0.38 | 07/09/26
TC52 | Subscription Data / Attributes – View Provisioned Asset Attributes | P2 | 4 | customer-hub/customer-management/account-details/subscription-data/services.page.ts | ⏳ Pending | 2.5 | 0.31 | 07/09/26
TC53 | Billing Data / Subscription Balance Inquiry – View Subscription Balances | P2 | 5 | customer-hub/customer-management/account-details/billing-data/bills.page.ts, customer-hub/customer-management/account-details/billing-data/balances.page.ts [NEW] | ⏳ Pending | 7 | 0.88 | 08/09/26
TC54 | Billing Data / Invoice Management – View and Manage Invoices | P2 | 11 | customer-hub/customer-management/account-details/billing-data/bills.page.ts, customer-hub/customer-management/account-details/billing-data/invoice-payment-installment.page.ts [NEW] | ⏳ Pending | 10 | 1.25 | 09/09/26
TC55 | Billing Data / Waybill Management – Inquiry and Transfer | P2 | 8 | customer-hub/customer-management/account-details/billing-data/bills.page.ts, customer-hub/customer-management/account-details/billing-data/lading-bill.page.ts [NEW] | ⏳ Pending | 8.5 | 1.06 | 10/09/26
TC56 | Billing Data / Transactions – View Transaction Detail and Recurring Data | P2 | 10 | customer-hub/customer-management/account-details/billing-data/bills.page.ts, customer-hub/customer-management/account-details/billing-data/transactions.page.ts [NEW] | ⏳ Pending | 9.5 | 1.19 | 11/09/26
TC57 | Billing Data / Rated Usage Inquiry – Filter Rated Usage Transactions | P2 | 6 | billing-hub/usage/usage-ops.page.ts [NEW], customer-hub/customer-management/account-details/billing-data/bills.page.ts, customer-hub/customer-management/account-details/billing-data/rated-usage.page.ts [NEW] | ⏳ Pending | 11.5 | 1.44 | 15/09/26
TC58 | Billing Data / Usage Records – Filter and Export Usage Data | P2 | 6 | customer-hub/customer-management/account-details/billing-data/bills.page.ts, customer-hub/customer-management/account-details/billing-data/usage-records.page.ts [NEW] | ⏳ Pending | 7.5 | 0.94 | 16/09/26
TC59 | Subscription & Billing Data / AR Request Log – Filter AR Requests | P2 | 6 | ar-hub/ar-operations/ar-operations/adjustment.page.ts [NEW], customer-hub/customer-management/account-details/billing-data/bills.page.ts, customer-hub/customer-management/account-details/billing-data/ar-request-log.page.ts [NEW], customer-hub/customer-management/account-details/subscription-data/services.page.ts | ⏳ Pending | 11.5 | 1.44 | 17/09/26
TC60 | Billing Data / AR Operation Units – Filter by Item ID | P2 | 5 | ar-hub/ar-operations/ar-operations/adjustment.page.ts [NEW], customer-hub/customer-management/account-details/billing-data/bills.page.ts, customer-hub/customer-management/account-details/billing-data/ar-ops-units.page.ts [NEW] | ⏳ Pending | 11 | 1.38 | 21/09/26
TC61 | Billing Data / Payments – Filter Payments by Date, Status, Reference and Invoice | P2 | 8 | customer-hub/customer-management/account-details/billing-data/bills.page.ts, customer-hub/customer-management/account-details/billing-data/payments.page.ts [NEW] | ⏳ Pending | 8.5 | 1.06 | 22/09/26
TC62 | Billing Data / Invoice Payment Due Dates – Filter Payments by Due Date and Invoice | P2 | 8 | customer-hub/customer-management/account-details/billing-data/bills.page.ts, customer-hub/customer-management/account-details/billing-data/invoice-payment-installment.page.ts [NEW] | ⏳ Pending | 8.5 | 1.06 | 23/09/26
TC63 | Billing Data / Credit and Debit Notes – Filter by Date Range and Note Type | P2 | 7 | customer-hub/customer-management/account-details/billing-data/bills.page.ts, customer-hub/customer-management/account-details/billing-data/credit-debit-notes.page.ts [NEW] | ⏳ Pending | 8 | 1 | 24/09/26
TC64 | Billing Data / Account Statement – Filter, Export and View Notes | P2 | 10 | customer-hub/customer-management/account-details/billing-data/bills.page.ts, customer-hub/customer-management/account-details/billing-data/account-statement.page.ts [NEW] | ⏳ Pending | 9.5 | 1.19 | 25/09/26
TC65 | Billing Data / Shared Charge Configuration – Create New Shared Charge | P2 | 5 | None (use existing) | ⏳ Pending | 3 | 0.38 | 25/09/26
TOTAL |  |  |  |  | 0 Done / 48 Pending |  |  | 25/09/26